# Coalisland & Dungannon Neighbourhood Renewal Area

# Annual Report 2022 – 2023

# Coalisland & Dungannon Neighbourhood Renewal Partnership

ANNUAL REPORT – 2022 to 2023

About Neighbourhood Renewal

The Neighbourhood Renewal Programme aims to reduce the social and economic inequalities which characterise the most deprived areas.  It does so by making a long term commitment to communities to work in partnership with them to identify and prioritise needs and co-ordinate interventions designed to address the underlying causes of poverty.  Neighbourhood Renewal Partnerships were established representative of local community interests together with appropriate Government Departments, public sector agencies, private sector interest and local elected representatives.

About Coalisland & Dungannon Partnership - Coalisland & Dungannon Partnership was set up in 2012 to take forward the Neighbourhood Renewal Programme and oversee the development and delivery of the local Action Plan.  In 2022/23 the Partnership comprised of up to 47 members which included representatives from local communities, voluntary organisations, elected representatives, private sector and local statutory organisations including NIHE, PSNI, SH&SCT and EA.  It meets on a bi-monthly basis (and as required) and its administration and facilitation is provided through a Coordinator who is based within the Mid Ulster District Council.

The Partnership has established 3 sub-groups to assist them in the identification, development and where appropriate delivery of projects which aim to address the Programmes’ 4 Strategic Objectives:

- Community Renewal

- Social Renewal

- Economic Renewal

- Physical Renewal.

They also assist the Partnership with the identification and delivery of projects and programmes in the Coalisland & Dungannon Neighbourhood Renewal Areas.   The Coalisland and Dungannon Partnership and Subgroup members have all signed up to the Neighbourhood Renewal Code of Practice and Guiding Principles and subsequent Subgroup Terms of Reference.

The Annual Report seeks to provide a summary of the level of activity taking place annually within the Neighbourhood Renewal areas, and demonstrate, as far as is possible, impacts and benefits derived from the NR investment.

Coalisland and Dungannon NR Partnership members 2022 to 2023

|  |  | Organisation | Status |
| --- | --- | --- | --- |
| Francie | Molloy MP | Partnership Chair | Elected Representative |
| Ann | Donaghy | Fairmount Residents Association | Voluntary & Community Rep |
| Annette | McGahan | PCSP | Statutory Representative |
| Barry | McGinley | Dungannon Youth Resource Centre | Voluntary & Community Rep |
| Bernadette | McAliskey | Belong An Tearman - STEP | Voluntary & Community Rep |
| Bronagh | O’Brien | SWC | Statutory Representative |
| Ciaran | McRory | Dungannon Thomas Clarke’s | Voluntary & Community Rep |
| Cllr Barry | Monteith | Councillor | Elected Representative |
| Cllr Clement | Cuthbertson | Councillor | Elected Representative |
| Cllr Dan | Kerr | Councillor | Elected Representative |
| Cllr Denise | Mullan | Councillor | Elected Representative |
| Cllr Dominic | Molloy | Councillor | Elected Representative |
| Cllr Joe | O'Neill | Councillor | Elected Representative |
| Cllr Kim | Ashton | Councillor | Elected Representative |
| Cllr Malachy | Quinn | Councillor | Elected Representative |
| Cllr Niall | McAleer | Councillor | Elected Representative |
| Cllr Niamh | Doris | Councillor | Elected Representative |
| Cllr Robert | Colvin | Councillor | Elected Representative |
| Cllr Walter | Cuddy | Councillor | Elected Representative |
| Colin | Ryan | PSNI | Statutory Representative |
| Colm | McDaid | Supporting Communities | Voluntary & Community Rep |
| Denise | McNally | Dungannon West Renewal Ltd | Voluntary & Community Rep |
| Dylan | Day | Ogras Youth Centre | Voluntary & Community Rep |
| Fintan | McAliskey | STEP | Voluntary & Community Rep |
| Jim | McQuaid | Dungannon Youth Resource Centre | Voluntary & Community Rep |
| Joanne | McDonald | CRAIC Arts Theatre | Voluntary & Community Rep |
| Joe | Connaghan | PSNI | Statutory Representative |
| Joe | Coney | MACP | Voluntary & Community Rep |
| Joe | McAree | DUY | Voluntary & Community Rep |
| John | Donnelly | Education Authority | Statutory Representative |
| John | Hagan | NIHE | Statutory Representative |
| Louise | McLaughlin | SureStart | Voluntary & Community Rep |
| Lucia | Carolan | Supporting Communities | Voluntary & Community Rep |
| Lucinda | McGinnis | Start 360 | Statutory Representative |
| Mark | Doran | Health Inequalities Officer MUDC | Statutory Representative |
| Mary | Coney | Department for Communities | Statutory Representative |
| Melanie | Campbell | Coalisland Development Assoc | Voluntary & Community Rep |
| Michael | McCrory | PCSP | Statutory Representative |
| Michael | McGoldrick | First Steps Women’s Centre | Voluntary & Community Rep |
| Monica | MacIntyre | Department for Communities | Statutory Representative |
| Oliver | Corr | CRAIC Arts Theatre | Voluntary & Community Rep |
| Richard | Thornton | Coalisland Training Services | Voluntary & Community Rep |
| Ryan | Patton | Department for Communities | Statutory Representative |
| Shane | McDonald | Ogras Youth Centre | Voluntary & Community Rep |
| Sinead | Taylor | SH&SCT | Statutory Representative |
| Siobhan | Wallace | SureStart | Voluntary & Community Rep |

Coalisland & Dungannon Neighbourhood Renewal Projects

The Neighbourhood Renewal Investment Fund supported 11 projects (1 of which is capital) in the 22/23 financial year, across the Coalisland & Dungannon Neighbourhood Renewal Areas.  Noted above, they are catalogued under the 4 strategic themes under NR as follows:-

Strategic Objective - Community Renewal

1. Dungannon & Coalisland Technical Assistance – Employment of Co-ordinator

Mid Ulster District Council lead the application to support the facilitation of the Partnership through the direct management of a NR funded Coordinator post. This post supports the Partnership in taking a lead in local planning, identification and implementation of agreed priorities and actions as set out in the agreed action plans - to tackle disadvantage and support the social, economic, community and physical development of the two local neighbourhood renewal areas.

During Covid, all meetings moved to an online platform.  Since then partners have expressed a preference for meetings to remain primarily online as they feel it is much more efficient as well as environmentally beneficial.

The Co-ordinator has managed the online meetings efficiently and effectively, providing support, guidance and monitoring.

The Co-ordinator provided support via digital platforms to communities, assisting in developing projects and worked in partnership with community organisations and relevant statutory agencies to ensure delivery and monitoring of the Action Plan.

The Action Plan is a mandatory item on both Partnership and Sub-Committee agendas and the Coordinator facilitates a review of this document on an Annual basis.

During the 22/23 year the Co-ordinator role has been responsible for:

- Circulating information regarding alternative and potential funding streams to organisations operating in the Neighbourhood Renewal Areas or signposting of services beneficial to partners and residents in the areas.

- Support and assistance to community groups including help with funding applications from other bodies.

- Applications were made to MUDC grant programmes and also levered in other funding. Appendix 1 details 40 Community & Voluntary Sector groups across a range MUDC grant programmes who have secure funding to deliver activity/benefit people living within the Dungannon & Coalisland Neighbourhood Renewal areas, securing over £193,644 in support.

- Coordination of bi-monthly sub group meetings for health, education and capital sub groups.

- Consultations with representatives from Department for Communities (DFC) and chairs of Neighbourhood Partnership and Sub Groups.

- Inviting guest speakers and other relevant stakeholders linked to the Programme along to speak at sub group and Partnership meetings on issues as required. Appendix 2 detail of the guest speaker/presentations to the Partnership and sub-groups over the year.

- Identifying and provision of training and development workshops to benefit Neighbourhood Renewal Partners, as required.

- Networking and meetings to publicise and promote Neighbourhood Renewal and raise awareness of the needs of the areas.

- The Coalisland & Dungannon Neighbourhood Renewal newsletter issued in early September 2022 and late January 2023 and contained a brief description of a number of NR funded projects being delivered. The newsletter is an excellent way of publicising the work of the partnership and the work various partners did during that period to all the communities to help raise awareness and gather support for the work being done in the NRA’s.

- Consultation with People & Place review team on co-design of the new policy for Neighbourhood Renewal.

The NR Coordinator post continues to act as a conduit between NR communities and DFC and the other stakeholders across the areas.

2. OGRAS – Disengaged Youth Programme

This project continues to engage vulnerable young people from Coalisland in youth development and social activity led by OGRAS Youth Club.  Engagement focuses on supporting young people participate in positive activity.  The base at Ogras provides for a range of activity to suit a range of needs.  The Youth Club works closely with a range of agencies to seek to attract people to the Club including linking schools in the area.  The range of activities the young people participate in includes; youth development work, drama, arts, sports and Irish language activities.

Up to 400 young people have benefited from this project during 2022 - 2023 which had the added outcome of developing 50 of the young people into volunteering work within and for their community. Activities included Young Men and Young Women projects which addressed needs based issues as identified by the young people themselves, excursions, motivational nights and a citizenship programme with St Joseph’s College Coalisland, World Mental Health Project and Resilience Programme.

A measure of its success and a reflection of the impact this programme has had on young people within the Coalisland Neighbourhood Renewal area over the past few years can be seen in the transformation of large numbers of young people engaged through this programme. This is clearly demonstrated in high numbers of youth progressing from being past participants of the programme to them securing roles as part-time members of staff who help deliver programme activity and support peer mentoring, most particularly including the summer scheme where over 250 young people participate over a 4 week period.

The engagement of young people in positive activity also contributes to their wider development in education, health and wellbeing and other engagement in their communities.

Recent activity carried out in 2022 - 2023:

- A fun day to celebrate the St Patrick’s Day festival was held on Friday 17th March.  Approx 420 people attended this event which had activities with Bouncy castles, Balloon modelling, Face Painting and Irish traditional music.

- 50 people engaged / involved in unpaid voluntary work in their community.

- A total of 435 young people engaged in and benefitted from youth inclusion / diversionary activities delivered by Ogras.

- Over 100 people received training in community development skills/capacity building.

- Outreach & Detached Work continued on Friday nights, where young people who were in danger of engaging in risk seeking behaviours were encouraged and supported to take part in activities being carried out in the Ogras Centre.

- Supporting personal development 10 young men participated in and completed the Drugs & Alcohol OCN accredited course.

It is very clear, year on year, that the service provided by Ogras, and supporting organisations remains an integral element in ensuring that the young people in the Coalisland Area are given the best possible chance at access to opportunities to move beyond the confines placed on them by living in an area of high deprivation and poverty. Impact felt is clearly visible when talking directly to those young people directly involved in the programme who are confident that their lives would have been dramatically different had they not had Ogras to turn to.

3. Mid Ulster District Council - Halloween Diversionary Project

The Coalisland Halloween Project creates diversionary activities for young people in the Coalisland area in the days and weeks leading up to Halloween itself. This initiative follows on from a successful project since 2012 which was identified through a community needs consultation when the project was designed to tackle anti-social behaviour in the area, which according to police data, peaks in October and accounts for 40% of all recorded crime in the area. Working in collaboration with local community and voluntary groups this project has over time reduced anti-social behaviour in the town.  The project is now led by a working group which was set up consisting of local sporting groups, local community / voluntary sector groups and is led by Mid Ulster Council. Anti-Social behaviour incidents in Coalisland have now fallen by 13.2% from 2012 and this group has transformed the Halloween period in Coalisland, from one which residents and families were fearing to one which they can now look forward to.

The Halloween Working group commenced weekly meetings early September and reports of ASB began to start up within the local area.  Ideas to find alternative diversionary activities, while keeping the youth safe, was discussed and a number of groups being funded under this programme.  Coalisland Fianna GFC organised a family fancy dress and magic show, Brackaville GFC held a spooky story telling family night.

OGRAS held a 5 day Spooky Trail which had 400 youth and parents through the trail and a fun day on Halloween day where 180 youth attended as well as the 50 young people who baked and gave out apple tarts as part of their ‘random act of kindness’ campaign.

Mid Ulster District Council organised an evening of entertainment when a significantly high number of community residents descended on Gortgonis playing fields on Monday 31st October 2022 for the funfair rides followed by the fireworks display.  These diversionary activities kept the young people off the streets in the weeks leading to Halloween, which reduced anti-social behaviour.

Strategic Objective - Economic Renewal

Strategic Objective: ‘To develop economic activity in the most deprived neighbourhoods and connect them to the wider urban economy’

4. Going Places with South West College – Coalisland / Dungannon NRA

This project involves the provision of dedicated services of three Mentors, who work together as a team, to cover all four Neighbourhood Renewal areas across the West, namely Enniskillen, Omagh, Dungannon and Coalisland.

Since March 2013 South West College (SWC) has supported community, economic and social inclusion within the Neighbourhood Renewal Area of Coalisland, Dungannon, Enniskillen and Omagh through the provision of the Going Places programme.  This Going Places Mentor-Led model recruits and engages residents of NRAs who face single or multiple barriers to progression to education and employment opportunities. The programme enables residents to participate in existing full or part-time provision of their choice where they will be mentored, supported and guided to fulfil their potential.

The initiative also seeks to engage residents who do not want to partake in long-term education, providing them with careers advice, employment options and short job-specific choices enabling residents to progress into employment.  Career led mentoring facilitates entry to employment and reduces the number of Job Seekers Allowance (JSA) Claimants in the four NRA areas. The variety of courses on offer to our participants is vast and allows us the opportunity to engage with both males and females in the NRA’s.

The project is aimed at residents aged between 16-64 years and allows us to not only focus on younger people, where there is currently a concentration of services, but also includes older people who have been identified as experiencing high levels of unemployment. It is aimed that participation in the programme will leave a long-term and positive “Lasting Legacy” through successful engagement in, and entry to, education and employment.

The one to one Mentoring support from a dedicated Going Places Mentor, helps residents remain on their course and gain a qualification which increases their chances of gaining and sustaining employment.   40 participants has taken part in the programme for 2022-2023. Following ongoing and regular evaluation of the Going Places programme throughout the 2022/23 Year the Going Places Mentor continues to be the key link in supporting participants with their progression, development and general health and well-being during the coming year.

The provision of support for mental health and well-being, resilience and confidence building will be vitally important to participants in the year ahead.  This will ensure that participants are supported and signposted to the relevant support agencies.

5. Coalisland Training Services – Community Education Programme

Over the year 2022/23, CTS Ltd continued to deliver a range of courses to the residents of Coalisland Neighbourhood Renewal area.

101 residents attended a variety of courses with 73 receiving formal qualifications. These have included CSR, Level 2 Food Safety, Paediatric First Aid, Emergency First Aid at Work, SAGE, and Essential Skills of Communication.

The residents who achieved Level 2 Communication qualification meant that they have met the eligibility criteria for their chosen career courses of Electrical and Plumbing. They will begin their courses in September 2023.  These two participants readily admitted that they had ‘messed about’ and tended to be ‘trouble makers’ at school. They were very appreciative of being given another chance with a tutor who had recognised their potential.

We also had a resident on CEP course (2022/2023) who we were able to secure employment for in Daycare nursery - this allowed him to join the Apprenticeship Childcare programme. He has recently achieved level 3 Apprenticeship Childcare qualification and has been promoted within his work.

Over the year, 14 residents have gained employment. These successes have been as a result of completing CSR; achieving SAGE or Level 2 Food Safety and Hygiene.  Two of these residents became self-employed; one as a joiner and the other in the frozen food delivery service.

This has also meant that 14 families have benefited, particularly in the current economic climate of the rise in the cost of living.  26 residents have enjoyed the social element of some of our courses. So while learning new art skills or improving existing skills; or for the ladies learning DIY skills or others who attended the camera club, these proved to be opportunities to make new friends or catch up with old friends.

They all help to spread the word about the golden opportunities available to residents of Coalisland Neighbourhood Renewal area and help us to recruit to our range of courses this year.   During this year CTS has also been able to signpost residents to possible funding opportunities based on their receipt of benefits.  This has proved to have had positive outcomes for a number of people who are now attending NVQ Diploma courses.

# Strategic Objective - Social Renewal – Education

6. Dungannon Social Renewal Education Programme

The Department for Communities NR funding provides funding to the Education Authority Southern Region to enable them, in turn, to deliver on identified need within the Action Plan. This Education project focuses on the Dungannon NRA. EA works alongside a number of stakeholders to deliver the following programmes to be delivered under this project;

- Primary Attendance Matters

PAMS is an early intervention model to support pupils, parents and schools by focusing on ensuring attendance is linked to the curriculum and parents are aware of the impacts of non-attendance.

2022 – 2023 programme didn’t take place due to EA Welfare Officers industrial action.

- STEP Numeracy and Literacy Programme

The STEP numeracy and literacy programme 2022 to 2023 aims to improve young people’s (age 7 to 14) communication skills in English.  Most children attending are from Eastern European backgrounds (Lithuanian, Poland, Russia and Bulgaria) and it targets the attainment of children in a language club, focusing on the development of both English and native languages and cultures.  The project has provided 30 children from minority ethnic backgrounds, organised in groups of 15-16 children in each with 4 hours of interactive support shared learning, social integration, and recreational activity each Saturday.

Project delivery is held in the shared community space of The Junction commencing beginning of October 2022.  Club staff update workbooks for beginner’s and continuously keep supporting parents and children in their learning at home process.  Staff continued to develop/review online teaching materials, whilst also producing hard copies of new Workbooks.  Project achieved targeted outcome of 30 NR area children participating pupils, who attained both face to face/ online activities each week. 30 parents engaged with programme and received support.

- DELTA / Family Learning Programme - Speech & Language Intervention Programme

St Patricks PS, Dungannon were able to offer and deliver their programme during 2022 to 2023.  Pupils from P1 and P2 who came from bilingual, multilingual and Traveller background were referred to the programme to help to improve speech and language skills.  Parents of selected children were contacted by letter and their permission to be included secured. Once the assessment of the pupil had been concluded, parents were then contacted by telephone and informed of the results and the outlined therapy recommendations. During the first term parents were discouraged from visiting the school to reduce risk and help ensure the school could remain open.

In term two a decision to offer on-site therapy using a booking system supported by office staff in school meant that parents attended individual sessions with their child on a weekly basis with the exception of Key Worker children who were already on site and attended on their own after the initial assessment with their parent.  All parents who participated in the programme continue to express their gratitude and thanks for the support the programme offers their children, and they report how the children enjoy the one-to-one sessions with the therapist.

24 pupils and 24 parents received support.

- Dungannon Youth Resource Centre Summer Scheme 2022-2023

Dungannon Youth Resource Centre is a full time voluntary youth club in the centre of Dungannon and has over 400 members.  The summer of 2022 was back to normality with our young people. A regular summer packed with adventure and activity. With no restrictions this summer we at Dungannon Youth Resource Centre got back to doing what we do best and that was putting on a great summer scheme program.

Our Summer Scheme ran from 3rd July 2022 to 6th August 2022 and over that period we engaged with 230 young people including 12 volunteers.  Summer Scheme began with volunteer training to prep for the summer scheme. We looked at the role of the volunteer, and what safeguarding measures we have in place for all staff and volunteers to follow.  This year it was good to see all the young people not having to worry about any restrictions or stressing about a virus they just carried on having fun with their friends, while encouraging good hygiene in general.

The scheme implemented:

- Get Active: One of our main priorities at Dungannon Youth Resource Centre is making sure the young people be active. This was a top identified need for young people. We had lots of indoor activities like sports day challenges that was suited for all ability levels. We also had a few big activity days at outdoor venues like the jungle were the young people got to experience the tree top walks, were we saw young people overcome their fear of heights which was rewarding to see. We also had our annual trip to the lake were the young people had fun on the massive water park. We done a bingo disco themed night for the young people where they had to get up and be active while playing bingo which went down a treat with staff and the young people.

- Relax:    young people enjoy relaxing with their mates at DYRC, and one of the ways of doing this is watching movies at the centre so we knew that if we booked some cinema trips, they would go down well with the young people, so we went and saw some good movies in the cinema which was great for all staff and young people to relax. We do have chill out areas at the centre which the young people also use to relax with their peers.

- Healthy mind and body: - AB COACHING, came in a delivered some sessions on looking after our wellbeing, the young people learned about being resilient and how being active and playing games can help our wellbeing. The young people learned four parts of looking after their mental health was to connect with each other so we are not alone, they also were taught to share any issues or problems they had so it would not be kept in, and they would have the support of friends and lastly, they were taught how believing in themselves can help them grow.

- Creativity: Being creative is a good way to get the mind flowing and thinking outside the box. We used ArtFunkle to let the young people create their own masterpieces on canvas. The young people were taught step by step how to create their own pieces. Art and crafts is a great way for our young people to build relationships as well as learn a new skill.  The young people designed the posters for our bingo loco night which was very bright and colour.

- Volunteers As always at DYRC we need our volunteer’s help, which is so valuable to not only the staff at the Centre but our young people as well. The volunteers are regarded as staff members, and this helps them with their own confidence as to be treated like an adult and a respected member of the team and not just as a young person. “I am more confident now that I have volunteered at the youth club, before I was too shy to help anyone now, I am more confident in helping large groups of kids and it was so rewarding, I felt so good” (volunteer summer 2022)

We had a great relationship with the local schools in terms of our volunteers. Some were recruited through the schools, and the rest from our own Centre which gives the younger members of the Centre a progression incentive to go on and volunteer and maybe in the future, employment. We had a great relationship with the local schools in terms of our volunteers. Some were recruited through the schools, and the rest from our own Centre which gives the younger members of the Centre a progression incentive to go on and volunteer and maybe in the future, employment.  We had 12 volunteers for our summer scheme. A few of those will move on to Higher Education but we expect to retain the rest of them to support us this year.

- Dungannon Youth Resource Centre - Youth Engagement programme – Mental Ability Projects 2022-2023

The theme of this project is to develop strategies in partnership with the young people to tackle the high rates of mental health, suicide and low self-esteem among youth in the Neighbourhood Renewal Area.  All the work that young people carried out this period was designed at improving their mental well-being with an eye on sharing the best parts of this with others.

Dungannon Youth Resource Centre ran two programs throughout the year focusing on Mental Health.  From this DYRC recruited two groups of young people - 15 of aged 9-13 and 15 aged 14-18.  Programmes will run around health and well-being focusing on identified need which has currently been stated by young people as:

- Healthy relationships

- Gambling

- Resilience

- Through the month of October and November DYRC worked with the 9-13 year olds focusing on all three issues

- Healthy relationships

- Gambling

- Resilience

Another programme ran in February over the course of a residential this work will continue.

DYRC worked with the 14-18 year olds on all the issues over the course of a residential at Halloween and a program in January and February.

Both groups will highlight, promote, and celebrate their learning in February/March.

- All young people will take part in:

- Workshop based sessions

- Educational visits/teambuilding activities

- Residential

- Awareness raising sessions

- Promotion of learning to peers and other DYRC members

DYRC monitors and evaluates all interventions and activities that the organisation undertakes with young people and records all interventions supported by video, photographic evidence and personal testimonies from stakeholders.  Through engagement of this programme the young people involved in the workshops, residential, healthy eating, fitness activities, feel good sessions and time out for themselves.  This has encouraged a more positive outlook on life and a better understanding of mental health.

- Transition Project

The Transition Project is offered in a one off session or three week basis.  The project aims to support P7 pupils with transfer related issues by enhancing the following:

- Develop new friendships and improve self esteem

- Ensure that pupils settle into new schools with less anxiety for themselves and parents

- Improve interest in school work and attainment

- Ensure the transition is successful by using mentors

- Ensure that curriculum continuity is achieved

2022 – 2023 programme didn’t take place due to EA Welfare Officers industrial action.

7. Coalisland Social Renewal Education Programme

The Department for Communities NR funding provides funding to the Education Authority Southern Region to enable them, in turn, to deliver on identified need within the Action Plan.  This project focuses delivery across the Coalisland NRA.  EA works alongside a number of stakeholders to deliver the following programmes to be delivered under this project;

- Cairde Uí Neill Adults Programme– Learning is Fun

This project enables parents, grandparents, close family relatives and carers to develop their knowledge of the Irish language to allow them to interact with their child and support and encourage them with any problems which they may have whilst doing homework. The Structure of the Irish Language classes offered by Cairde Uí Neill are from Beginner through to Advanced and these levels allow parents and family members to enhance their own Irish language skills and to be able to assist their children.

During 2022-2023, tuition continued to be delivered through a hybrid approach i.e. online/ face to face classes in Gaelscoil Uí Néill.  There were an estimated 94 pupils engaged from beginners level to advance level on the programme through the regular help and interaction of their relatives/carers. The classes continue to be a great success with large numbers participating and many of our students go onto higher learning via the Ulster University Part-time courses - Diploma and BA Hons degree courses in Irish Language and Literature.

More of our students are preparing to go onto higher learning in 2022-2023 via the Ulster University Part-time Diploma in Irish as well as the BA Hons Degree in Irish Language and Literature.

Cairde Uí Néill promote classes through their website and social media channels – Facebook, Twitter and Instagram. The group also use the local parish bulletins and the press.

- Primate Dixon Parenting Programme

This programme is aimed at parents and skills development within the family at Primate Dixon primary school.  The focus of the programme in 2022-2023 was a school based speech and language programme for pupils in Primary 1 and 2 classes displaying difficulties in communication.  Pupils are identified as requiring speech and language therapy and parents were involved in the success of the programme, including a ‘Bring your Parent to school day’, monitoring of homework and ensuring attendance at therapy sessions.

The Primate Dixon PS NRA speech and language programme 2022-2023 commenced early October with Speech Therapist assessments taking up to 2 weeks to complete.  Support was offered to 20 families of P1 and P2 pupils.

Speech Therapists provided a wide range of support programmes for teachers and especially children – these formed part of Learning Packs, Google Classroom and other programmes. This support has been invaluable to both children, families and teachers.

Children in need of support this year were again identified through a process of consultation with school SENCO, classroom teacher and very importantly parents.

Information regarding needs was shared with the Specific Learning Difficulty (SpLD) Therapist. Children in Nursery and Primary 1 year groups were the priority, a total cohort this year of 135 children, of whom around 40% children need support at varying but including intensive levels. NRP’s additional funding enabled the provision of remote learning and support activities for almost 60 children and also for 8 other children from Primary 2 to Primary 7.  Sessions were able to take place weekly over periods on six weeks. NRP funding enabled the school to double the number of six-week blocks. This was invaluable and was making a great difference for children. There continue to be many positives from the SpLD programmes available in the school. Almost 60 children have benefitted growing early language skills.  Parents have been further enabled to deliver and reinforce activities at home. All parents who participated in the programme continue to express their gratitude and thanks for the support the programme offers their children, and they report how the children enjoy the one-to-one sessions with the therapist.

- An Tearmann – Homework Club

This project provides a homework club and additional learning skills for members of the travelling community and links this activity with improved attendance and achievement in school.   On-site Homework Club activities were delivered online by support workers. They prepared additional teaching materials and workbooks for work from home.  Scrapbooks were introduced and are now used as a method of recording good practice and children’s work.  A number of sessions were organised to help develop the children’s ability to talk about their own feelings, and how to best express themselves.  It has been identified that P6 - P7 students required more support with homework prior to the transfer test with a possibility to extending this service in the future.

The relationship with parents is excellent and they are enthusiastic about registering their children for homework help. They have a good relationship with the staff which also creates an opportunity for parental support in other areas.

During 2022-2023 there were approximately 38 Traveller Children registered with An Tearmann Homework club with 34 children demonstrating improvements in behaviour.   This year saw a greater level of parental engagement over a more prolonged period of time. In addition more parents taking up the opportunity of adult literacy class.

- OGRAS - Summer Scheme (Youth Intervention)

The aim of this project is to address the issues around community relations in helping manage the levels of anti-social behaviour over the summer months and to provide for children and young people an engagement in positive activities.  The project also addresses a range of issues related to poverty including isolation through not being able to participate with peers, mental health, and summer hunger.

The programme has provided high numbers of young people with opportunities to participate in activities and go on trips with other young people during the long summer period.  With many of these young people coming from a disadvantaged background this is their only "Summer Holiday" and a high point of the summer.  Parents are appreciative of the opportunity offered their children during this scheme.  A key benefit of the scheme is that the young people are provided with a healthy meal which addresses the growing issue of "Holiday Hunger" for those children/young people that are in receipt of free school meals during term time.

5 registration nights were organised and two main elements were for junior and senior schemes but this year for the first time we included an Inclusion Scheme and a Camping Trip.

Inclusion Scheme One week for Young People with Additional needs, 10 young people with complex needs attended.  From Monday 8th August to Friday 12th August 2022 activities included team games and art, petting farm, Tamnamore Gardens, Artfunkle and a BBQ party.

Camping Trip

30 seniors enrolled and got an opportunity to experience this Trip were they challenged their fears and examined community based work.

From 11th to 13th August 2022.

Junior

2 Week long Summer Scheme, from Monday to Friday each week day from 9.30am to 1.30pm from 18th July to 29th July 2022.  Activities and trip included fun day, Artfunkle, kid’s farm, Lisburn LeisurePlex and Splat Attack.  Daily attendance/membership at Junior summer scheme was 400 membership with an average attendance of 260 young people per day.

In addition to these organised trips a variety of other activities were available to play, such as mini games, badminton, indoor soccer, pool, table tennis. We also offered a number of arts & crafts and drama workshops.

Senior Summer Scheme

Senior summer scheme has 200 members which attracted approx 120 young people per day which ran from 12.00 noon until 4.00pm from Monday 1st August to Friday 5th August 2022.  Trips and activities included the following; Fun day, petting farm, Lake Kilrea, M&D’s Theme Park in Scotland and BBQ party.  As with the junior Scheme, the seniors were also able to avail of multi-sport options alongside Arts & Crafts and drama workshops.

Tony Murphy (Acting Director DfC) called with Ogras on Friday 5th August and stated “he was very impressed with all the work that Ogras do and especially with the Inclusion work with Young People with Disabilities and the Traveller Community.’    He was also very encouraged by the fact that many of the staff including ourselves have grown up with the Youth Club and had completed the cycle as mentors, Volunteers and then Employee’s

8. Education Authority – Coalisland & Dungannon Neighbourhood Renewal Area Learning Mentor

DfC funded a full time Learning Mentor post who is employed on behalf of five Post-Primary Schools serving the Coalisland/Dungannon Area.  The learning mentor works across each of the schools supporting specific children in achieving their unique potential: academically, socially and emotionally.  The project primarily targets young people who live in Neighbourhood Renewal areas and those who have been identified by their schools as being at risk of underachievement in learning and development.

The learning mentor supports pupils and parents throughout the year.  The programme is not only to work with the young people but to break down communication barriers between home and school, developing a positive link to help enhance the potential of those involved. This programme helps to develop the self-esteem and confidence of the young people who avail of it.  Alongside this, programmes are held for parents in relation to how they can best support their child during assessment phases and examinations.

The NR Area Learning Mentor delivered during the financial year April 2022 to March 2023 the following:

- One-to-One Mentoring offering support for attendance, attainment and behaviour (both in person and virtually)

- Learning Together Workshops for Key Stage 3 & 4 pupils and parents

- Peer Mentoring was provided for 30 pupils in English, Maths and Science

- Polish & Portuguese Language Club – 6 week session in Term 1 & Term 2

- Year 8 Maths Club

- Year 14 Interview Skills Workshops

- Year 8 Transition workshops in St Patrick’s College and St Joseph’s Grammar

- Learning to Learn Pupil Workshops

- “Acceptance” workshop delivered to Year 12 in St Joseph’s Grammar

- A Grade Enhancement Programme run for St Patrick’s Academy, whereby Learning Mentor worked with students in across a range of subjects in preparation for assessments

- Year 10 programme – “Preparing for GCSE – Numeracy” supporting students with the basic concepts of numeracy before they transition to GCSE Maths in September

- “Being Prepared to Learn” workshop for group of Year 9 students, helping them manage their time better/complete their work/manage their emotions during remote learning.

9. St Joseph’s Vocational Project

The Improving Engagement and Attendance Programme was previously aimed at pupils whose school attendance has fallen below the expected 95%.   The majority of the pupils selected for the programme fell below this percentage with the exception of a few, who were selected for pastoral reasons.  The programme has allowed our 20 students who were displaying, attendance and behaviour concerns   to engage in a vocational programme allowing them to develop interpersonal, develop their emotional resilience and enhance work related skills to allow them the opportunity to be able to make good choices for their future work prospects.

This year 10 boy and 10 girls were selected to engage in the 22 week programme from Year’s 9 and 10.  These were pupils who had already had difficulties with attendance and engagement, and were also seen as candidates who may be more suited to this programme to get a taste for a job related programme.  Their overall attendance improved and this was because of their engagement in the programme.  These pupils made a concerted effort to be in school on the day of the programme.

The Leader of Pastoral Care and Community, the Attendance and Lesson Monitor Co-ordinator and the Head of Upper Key Stage 3, looked across all the information in consultation with the SENCO and Leader of Learning to establish the current needs of our students.  The staff involved worked on the needs of the pupils and the knowledge they had of the pupils and how it would enhance/improve their attendance, engagement, behaviour and opportunities for future work.   A number of pastoral issues were noted with regards self-esteem, building confidence and resilience, giving these pupils the opportunity to enhance their potential for the working world.  The students engaged in a number of elements where boys participated in Bricklaying, Joinery and some Electrical work and girls engaged in Hairdressing and Beauty.

The level of attendance at CTS for the Improving Engagement and Attendance programme was excellent this year. Both the tutors and the school noting the progress made by pupils, in attendance, behaviour and attitude to work. There will be a presentation of certificates for the completion of this programme at the upcoming Key Stage 3 Awards Ceremony.

Strategic Objective - Social Renewal – Health

10. Coalisland and Dungannon NR Health and Social Well Being Programme

The Coalisland and Dungannon Health project is led by the Southern Health and Social Care Trust in conjunction with a health subgroup which meets on a regular basis to research, develop and monitor health needs in the NRA’s and wider areas of Coalisland and Dungannon.  The outcomes of the subgroup are adopted and formulated into the overall NR Action Plan on an ongoing basis.

The subgroup includes representation from Statutory, Community and voluntary agencies to include: Mid Ulster District Council, DfC, SHSCT, Start 360, Coalisland Residents & Community Forum, Ógras, Dungannon Youth Resource Centre and LiLAC.  The Subgroup supports effective partnership working between agencies and the community, developing a targeted health action plan which is linked into the overall Neighbourhood renewal action plan for the area.

The need for these programmes in the NRAs are stark, with the programmes designed to offset the health realities experienced by people living in Neighbourhood Renewal Areas, some examples of which are listed below:

- large inequality gaps continue to exist for mental health indicators. Prescription rates for mood and anxiety disorders increased regionally and for most & least deprived areas between 2017 and 2021, with the rate in the most deprived areas 66% higher than in the least deprived areas. In 2019-21 the suicide mortality rate in the most deprived areas was more than double that observed in the least deprived areas.

- alcohol and drug related indicators continue to show some of the largest health inequalities monitored in NI, with rates in the most deprived areas over five times that in the least deprived for deaths due to drug misuse and four times that for alcohol specific mortality.

- in 2021, within the most deprived areas the proportion of births where the mother reported smoking during pregnancy was almost five and a half times the rate in the least deprived areas.

- over the last five years the inequality gap in the proportion of Primary 1 children classified as obese widened from 45% to 93% due to an increase in obesity rates in the most deprived areas while rates in the least deprived areas saw no notable change.

The programme also offers other programmes to improve the general health of the populations of the NRAs, including gambling counselling, therapies, cancer screening, first aid and many more.  The number of users availing of the programme has grown

- South Tyrone Men’s Shed

South Tyrone Men’s Shed (also known as Dungannon Men’s Shed) has a membership of 32 men and provides a safe environment where their members meet, socialise, share skills and learn new skills.  The group are a voluntary self-help team who actively encourages members to express themselves mentally and physically through arts, crafts and planned activities

With an aim to prevent social isolation, particularly but not exclusively for men aged 30 and over, the group integrate into society through the provision of facilities by undertaking creative, physical, recreational activities, learning and passing on skills and knowledge to support each other socially.

Recently the group had the opportunity to work in partnership with ArtsEkta on a project funded by Peace IV along with Mid-Ulster District Council, Washingbay Sheds and Blackwater Community Barge in designing and supplying Wheelchair friendly picnic tables.  This project was funded by Peace IV.

South Tyrone Men’s Shed make many wooden garden crafts, such as picnic tables, 3-seater summer seats, 3-seater swing seats, donkey cart planters, raised flower beds and planters, bird feeder tables, dog kennels and picket fencing for Santa Claus!   This year they delivered an advance wood turning programme and wood carving programme.

 Coalisland Men’s Shed

Coalisland & Loughshore Men’s Shed has a membership of 52 men and is a service run by Lilac to support men who want to come together to share, care and learn new skills in a safe place.  It aims to prevent social isolation and help improve the well-being and mental health of all its members.  With the venue and facilities upgraded for wheelchair access, this is a great opportunity for men to socialise, talk and connect with other while taking part in group projects, in creating raised flowerbeds, craft pieces such as flower boxes, trellis, bird and owl boxes, picnic tables, to growing their own fruit and veg.

This year members delivered a horticulture programme and a number of health and wellbeing initiatives including footgolf, walking groups and arts projects and also supported ‘Meenagh Park in Bloom’ and participated in a range of online classes and tutorials.  The participated in healthy eating and baking programmes.  They held a Men’s Health MOT with a total of 22 men getting Blood Pressure and Cholesterol checks completed, as well as receiving very useful health information from O’Neill Pharmacy who deal with minor ailments and advised members to contact their GP to help deal with more serious issues.

The Lady’s Garden Club has now been established with tutorials held on a Tuesday and Thursday mornings on how to sow seeds, potato growing, hanging baskets and recycling in the garden.  Botanical Art classes are also available.

 LILAC

Using a blended approach Lilac provided 76 people from within Dungannon and Coalisland NR area with complimentary therapy sessions to clients suffering from long term chronic health conditions.  These sessions included reflexology, art or gardening to improve their health and wellbeing, talking and art therapies and helped reduce reliance of medication and promotes well- being through alternative options, offering those in need greater choice and control over their illness. Introducing on line therapies also enabled LILAC to provide a ‘stepped care’ approach to future clients matching the intensity of the treatment to their needs.  During this period LILAC also launched ‘Living Well Coalisland’ a Health Hub in Coalisland’s Neighbourhood Renewal area.

These complimentary therapies to help alleviate the emotions and symptoms that often accompany the diagnosis and treatment of cancer. Each individual has different needs and the team works with the client to put together a package to help relieve their burden.  Many users reported that therapies help relieve conditions of anxiety, fear, nausea, aches and pains, depression and insomnia. Therapies are designed to work alongside conventional treatment. The centre provides a welcoming and confidential environment where people receive high quality support services for Health and Wellbeing.

 House of Health – Menopause Programme

The Menopausal Awareness Programme was delivered by Craic to women from Coalisland and Dungannon and surround areas.  The 6 week programme built on the information on menopause as discussed on the information night.  Facilitators provided physical activity, information and discussions on complimentary therapies, nutrition, stress management, mental health and included support to put all these things together to improve individual’s lives and sense of wellbeing.  The feedback was been so positive and individuals have shared how much a difference it has made to them not feeling alone.  Overwhelmingly the key message is that women want to get out and get support from people going through the same thing.

As a result of the relationships built and support received, the women want to continue with support from peers.  They have created a new group called Wild Flowers, launched in mid-March 2023 and it has over 200 members already and a meet up walk was arranged at the end of March in Dungannon Park which was very well attended.  There is so much demand at present for support and women who at the start of the program felt not listened too now have had the strength to contact their GPs and are now receiving treatment that has vastly improved their quality of life.

 House of Health – Early Intervention – Incredible Years

The Incredible Years Programme is a series of set programmes for children and parents, designed to improve children’s social, emotional and behavioural skills, which was delivered by STEP.  The programme provided to 10 families, aimed to help strengthen parent management skills, improve children’s social competence and reduce possible behaviour problems and reduction of conflict with parents at home.   This helped with children’s ability to make friends and have a better understanding of their own and others feelings, with a better ability to deal with conflict and improve willingness to learn.

# Strategic Objective - Physical Renewal

11. Capital Development

11.1	Dungannon Thomas Clarke’s

Capital Development Funding was secured via Mid Ulster District Council from the Department for Communities for Dungannon Thomas Clarke’s Community Sports Hub.  The project, led by Mid Ulster District Council on behalf of Dungannon Thomas Clarke’s with the support from the Dungannon Neighbourhood Renewal Partnership, will create a more fit for purpose shared community facility that will work to enhance and promote health and well-being opportunities for local people.

Communities Minister Deirdre Hargey along with MUDC Chair, Cora Corey and Chair of CNR DNR Partnership, Francie Molloy MP, Chair of Dungannon Thomas Clarke’s, John McNulty cut the sod on site of O’Neill Park Pavilion on Thursday 29th September 2022, for the commencement of the new health and community hub project.  The contractors demolished the old building and swiftly commenced construction of the new building, which by the end of March 2023 is nearing completion.  Hand over is due end of May early June 2023.

DfC Neighbourhood Renewal Programme secured Capital funding of £972,817 for the £1,145,945 total project cost which will see a purpose-built community and leisure facility replacing the outdated changing and meeting rooms, which were no longer fit for purpose.

The new facility will be a community complex incorporating a range of services to support:

- Community hall to cater for a wide range of events such as health and wellbeing activities, community and social events, music sessions, dance groups and general community meeting space.

- Fitness suite for health and wellbeing.

- Changing areas – to cater for all users of the facility in particular female provision, schools’ use, gym users, youth groups and the community who make use of the facilities for games and events such as sports day.

Photo below is the cleared site			   	Photo below is the steel framework

Front view of new building				Back view of new building

11.2	Gortgonis Health & Wellbeing Hub

Mid Ulster District Council have sought planning permission for a new community health and wellbeing hub on the site of the existing leisure centre in Coalisland.  The new facility will include a 225 seater community hall, a fitness suite, day care facility and a new 3G synthetic pitch and 6 lane running track.

DfC Capital Development Funding for 2021 – 2022 was delayed during the financial year due to technical issues arising with other statutory agencies.   However, 2022-2023 DfC confirmed there will be no Capital Funding available for this financial year due to cut back in public spend due to the Cost of Living Crisis.  Funding allocation from DfC remains uncertain for the future.

11.3	Coalisland Public Realm Scheme

DfC funded public realm scheme has been completed in Coalisland Town Centre which has transformed the town.  The £4.27m investment has created a significant physical enhancement and has created a safe, high quality and pedestrian friendly environment while improving traffic flow and parking around the town.

11.4	Coalisland Canal

DfC Covid 19 Recovery - Small Settlement Regeneration Prog for Coalisland Canal is now completed.  The funding provided an upgrade to the existing off road path network of 6.5km, to allow for a walking and cycling trail that will encourage more community and recreational activity in this rural area.  The £519K investment on the canal tow path has added to the numbers who already use it.

11.5	Revitalisation – Shop Front Improvement Scheme

The Shop Front Improvement Scheme offered grant matched funding to local Coalisland and Dungannon businesses to spend on renovation and modernisation of shop fronts in and around the High Street area. The improvements facilitated by the scheme included renovation works to improved signage, shop branding, and lighting.

Coalisland & Dungannon Neighbourhood Renewal Partnership 2022 - 2023 Expenditure (by Strategic Objective)

The following table details current projects funded via the Neighbourhood Renewal Investment fund.  It also details the 22/23 individual spend for each project, the total amount of expenditure by strategic objective and the overall 22/23 total expenditure in the Coalisland & Dungannon Neighbourhood Renewal Areas.

| Programme/Project | CFF Funding Period | CFF amount at 01/04/2022 | 22/23 Spend (as at 31/03/23) |
| --- | --- | --- | --- |
| COMMUNITY RENEWAL |  |  |  |
| Coalisland and Dungannon Employment of Neighbourhood Renewal Coordinator(including Coalisland Halloween Diversionary Event) | 01/04/2022 – 31/03/2023 | £42,389.33 | £40,097.66 |
| Disengaged Youth Programme in Coalisland | 01/04/2022 – 31/03/2023 | £42,314.67 | £42,314.67 |
| Total Community Renewal Expenditure |  | £84,704.00 | £82,412.33 |

| Programme/Project | CFF Funding Project | CFF amount at 01/04/2022 | 22/23 Spend (as at 31/03/23) |
| --- | --- | --- | --- |
| SOCIAL RENEWAL - EDUCATION |  |  |  |
| Dungannon Social Renewal Education Programme | 01/04/2022 – 31/03/2023 | £51,033.40 | £44,003.92 |
| Coalisland Social Renewal Education Programme | 01/04/2022 – 31/03/2023 | £61,219.90 | £61,219.90 |
| St. Joseph’s Vocational Project | 01/04/2022 – 31/03/2023 | £26,500.00 | £26,500.00 |
| Dungannon and Coalisland Learning Mentor | 01/04/2022 – 31/03/2023 | £73,896.83 | £72,864.11 |
| Total Social Renewal Ed Expenditure |  | £212,650.13 | £204,587.93 |

| Programme/Project | CFF Funding Project | CFF amount at 01/04/2022 | 22/23 Spend (as at 31/03/23) |
| --- | --- | --- | --- |
| SOCIAL RENEWAL HEALTH |  |  |  |
| Coalisland & Dungannon NR Health and Social Wellbeing Programme | 01/04/2022 – 31/03/2023 | £43,938.95 | £43,938.95 |
| Total Community Renewal Expenditure |  | £43,938.95 | £43,938.95 |

| Programme/Project | CFF Funding Project | CFF amount at 01/04/2022 | 22/23 Spend (as at 31/03/23) |
| --- | --- | --- | --- |
| ECONOMIC RENEWAL |  |  |  |
| Going Places with South West College | 01/04/2022 – 31/03/2023 | £56,835.41 | £52,213.34 |
| Coalisland Community Education Programme | 01/04/2022 – 31/03/2023 | £28,999.55 | £28,999.55 |
| Total Economic Renewal Expenditure |  | £85,834.96 | £81,212.89 |

ACHIEVEMENTS OF NEIGHBOURHOOD RENEWAL

FUNDING IN 2022/2023 YEAR

Community Renewal Output Measures to be used for 22/23 Annual Report

| PROJECT | CR1 - Number of people participating in community relations projects | CR2 – Number of people participating in community bonding projects | CR3 – Number of people volunteering for community development activities | CR4- Number of people engaged/involved in unpaid voluntary work | CR5 – Number of people receiving training in community development skills/capacity building | CR6 - Number of people using new or improved community facilities | CR7- Number of community/voluntary groups supported | CR8- Number of community relations projects supported | CR9 - Number of people involved in projects that promote shared space | CR10 - Number of people using existing community facilities | CR11 - Percentage of residents who say they are aware of community facilities/services in their area |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Disengaged Youth Programme in Coalisland | 410 | 360 | 95 | 95 | 50 | 230 | 55 | 10 |  |  |  |
| Coalisland Halloween Diversionary Event | 550 | 44 | 50 | 50 | 50 |  | 3 |  |  | 550 |  |
| Social Renewal Education Programme Coalisland NRA | 50 |  |  | 50 |  |  |  |  |  |  |  |

Economic Renewal Output Measures to be used for 22/23 Annual Report

| PROJECT | ER1 - Number of FTE permanent jobs created | ER2 – Number of residents going into employment | ER3 – Number of people accessing careers advice | ER4- Number of people receiving job specific training | ER5 – Number of weeks (per participant) of job specific training provided | ER6 - Number of people receiving non job specific training e.g. first aid | ER7- Number of weeks (per participant) of non-job specific training provided | ER8- Number of new business start ups | ER9 - Number of new/existing businesses requiring/receiving advice/support | ER10 - Number of people becoming self-employed | ER11 - Number of Social economy enterprises created/supported | ER12 - Number of new business start-up surviving 52 weeks | ER13 - Number of new/existing childcare places supported to facilitate training and or employment | ER14 - Number of people attaining a formal qualification from participation in Adult education | ER15 - Number of FTE jobs safeguarded |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Going Places with South West College |  | 40 | 40 | 35 |  |  |  |  |  |  |  |  |  | 30 |  |
| Coalisland Community Education Programme |  | 15 | 73 | 30 | 30 | 10 | 30 |  |  |  |  |  |  | 71 |  |
| St. Joseph’s Vocational Project |  |  |  | 20 |  |  |  |  |  |  |  |  |  |  |  |

Social Renewal Education Output Measures to be used for 22/23 Annual Report

| PROJECT | SR(Ed) 1 - Number of childcare/nursery school places crated/safeguarded | SR(Ed)2 - Number of pupils whose attendance is measurably enhanced/improved | SR(Ed) 3 - Number of pupils whose attainment is measurably enhanced/improved | SR(Ed) 4 - Number of pupils whose behaviour is measurably enhanced/improved | SR(Ed) 5 - Number of people engaged in parenting skills development programmes | SR(Ed) 6 - Number of pupils directly benefitting from the project | SR(Ed) 7 - Number of pupils whose attainment is measurably enhanced/improved | SR(Ed) 8 - Number of pupils directly benefiting from project | SE(Ed) 9 - Number of pupils whose attainment is measurably enhanced/improved (in STEM subjects) | SR(Ed) 10 - Number of pupils directly benefitting from the project | SR(Ed) 11 - Number of pupils whose attainment is measurably enhanced/improved against baseline position to ensure pupils reach full potential | SR(Ed) 12 - Number of pupils whose attendance is measurably enhanced/improved | SR(Ed) 13 - Number of pupils whose attainment is measurably enhanced/improved against baseline position | SR(Ed) 14 - Number of young people directly benefiting from the project | SR(Ed) 15 - Number of young people experiencing improvements against baseline position of assessed needs | SR(Ed) 16 - Number of young people having access to specialist support to address assessed needs | SR(Ed) 17 - Type and number of accredited qualifications completed | SR(Ed) 18 - Number of pupils directly benefitting from /being supported by the project | SR(Ed) 19 - Number of pupils whose attainment is measurably enhanced/improved against baseline position | SR(Ed) 20 - Number of children and young people having access to specialist support to enhance their physical and emotional well-being | SR(Ed) 21 - Impact on enhanced learning environment | SR(Ed) 22 - Increased number of young people and adults taking part on regular physical activity | SR(Ed)23 - Number of pupils whose attainment is measurably enhanced/improved (in ICT related subject) | SR(Ed)24 - Number of residents in an area who obtain a (ICT-related) qualification on completion of formal training | SR(Ed)25 - Number of pupils directly benefiting from project |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Dungannon Social Renewal Education Programme |  |  | 35 |  | 25 | 225 |  |  |  |  |  |  |  | 236 |  |  |  |  |  |  |  |  |  |  |  |
| Coalisland Social Renewal Education Programme |  |  |  | 22 | 56 |  | 20 |  |  |  |  | 30 |  | 376 |  |  |  |  |  |  |  |  |  |  |  |
| St Joseph’s Vocational Project |  | 20 |  | 20 |  |  |  | 18 | 20 |  |  |  |  | 20 |  | 20 |  | 20 |  |  | 20 |  |  |  |  |
| Coalisland/ Dungannon Learning Mentor |  | ### 11 | ### 41 |  | ### 60 | ### 221 |  |  | ### 30 |  | ### 22 |  | ### 20 | ### 221 |  |  |  | ### 57 |  |  | ### 20 |  |  |  | ### 20 |

SR(Ed) 1 – Early Years, SR(Ed) 2 – 5 - Tackling Barriers to Learning, SR(Ed) 6-7 Improving Attainment in Literacy and Numeracy, SR(Ed) 8-9 - Closing the Performance Gap, SR(Ed) 10-11 - Tackling barriers to Learning Special Educational Needs,  SR(Ed) 12-13 - Tackling barriers to learning Emotional Health and Wellbeing, SR(Ed) 14-17 - Youth Services,  SR(Ed) 18-22 - Extended Schools, SR(Ed) 23-25 - ICT

Social Renewal - Health Output Measures to be used for 22/23 Annual Report

| PROJECT | SR(H)1 - Number of people benefiting from Healthy Lifestyle Projects | SR(H)2 - Number of people attending Health Education/Awareness initiatives | SR(H)3 - Number of people accessing intervention/treatment services | SR(H)4 - Number of health education awareness initiatives provided/delivered | SR(H)5 - Number of people benefiting from new or improved health facilities | SR(H)6 - Number of people participating in suicide prevention projects | SR(H)7 - Number of new/improved sports facilities provided | SR(H)8 - Number of people using new sports facilities | SR(H)9 - Increase (n%) in the number of people using improved sports facilities |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Coalisland / Dungannon Health Project | 35 | 120 | 40 | 3 |  |  |  |  |  |

Social Renewal - Crime Output Measures to be used for 22/23 Annual Report

| PROJECT | SR(C)1 - Number of people receiving advice on crime prevention | SR(C)2 - Number of community safety initiatives implemented | SR(C)3 - Number of people participating/attending community safety initiatives | SR(C)4 - Number of crime prevention initiatives implemented | SR(C)5 - Number of people participating/attending crime prevention initiatives | SR(C)6 - Number of young people benefiting from youth inclusion/diversionary projects | SR(C)7 - Number of victims of crime supported | SR(C)8 - Number of homes with increased security | SR(C)9 - Number of Neighbourhood Wardens supported | SR(C)10 - Number of people involved in dealing with the impact of Interface issues |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Disengaged Youth Programme in Coalisland RW/NR3/CLD50B |  |  |  |  |  | 150 |  |  |  |  |
| Coalisland Halloween Diversionary Event – CLD58B |  |  | 450 |  |  | 450 |  |  |  |  |

Coalisland and Dungannon Partnership Conclusion

# In the 22/23 financial year, Coalisland & Dungannon Partnership total overall spend was £412,152.10.

This can be further broken down into Strategic Objective spend as follows:-

Community Renewal		£82,412.33

Social Renewal (Education)	£204,587.93

Social Renewal (Health)		£43,938.95

Economic Renewal			£81,212.89

# Breakdown of actual achievements for total expenditure

To take forward the Neighbourhood Renewal Programme, Coalisland & Dungannon Partnership was set up in 2012 to oversee the development and delivery of the local Neighbourhood Renewal Action Plan.  The Partnership currently comprises representatives from local communities, voluntary organisations, elected representatives, private sector and local statutory organisations including NIHE, PSNI, SH&SCT, Transport NI.  It meets on a monthly basis and its administration services are provided through a Coordinator with Mid Ulster Council.

The Partnership established 3 sub-groups to assist them in the identification, development and where appropriate the delivery of projects which aim to address the 4 strategic objectives of community renewal, social renewal, economic renewal and physical renewal.  They also assist the Partnership with the identification and delivery of projects and programmes in the Coalisland & Dungannon Neighbourhood Renewal Areas.

# As a Partnership there has been many successes that have been widely documented and we have also been successful with levering in other funding to our areas e.g. MUDC grants and significant capital commitment to the Gortgonis Project.  All of the above has meant added value has been linked to the Neighbourhood Renewal funding drawn down by the NR Partnership through Department for Communities to bring additional benefits to the NRA communities including Coalisland and Dungannon Public Realm along with investment in Coalisland Canal Tow Path.

# The NR programme has benefited the residents through the establishment of a co-ordinated approach to statutory delivery mechanisms.  The NR programme through its structures brings together a wide range of statutory bodies who share ideas and best practice from other areas.  For example, the Education programme has benefited from the key worker working across many NR areas.  Best practice projects are shared across the areas and rolled out where funding permits. The structure of the NR Partnership in many ways mirrors Community Planning at the local micro level.

# Recent deprivation statistics show that super output areas falling under the NRA have improved and are no longer within the top 10% deprived areas in NI.  Ballysaggart Super Output Area in Dungannon has fallen out of the top 10% to almost 27%.  Whilst there are many factors that have led to this it is not beyond the realms of possibility that the programme has had a significant impact in improving lives and reducing poverty in the NRA through the delivery of many programmes aimed at reducing inequalities, improving educational attainment and promoting healthy lifestyle programmes. Demographic factors are potentially another contributing factor given the significant migrant population that have settled in the area and as mainly economic migrants may not engage in mainstream statistical count recording.

Priorities for 22/23 are to ensure funding continues for all the current projects and efforts are made to plan for sustainability beyond the lifetime of NRA funding.  There remains a need to put greater focus on recognition of the impact these projects have had in the two NRA’s over the past decade or so and consider how best this impact can be captured.  Ensuring that the projects are sustained in some way is crucial for the Partnership leading in to next year.  There needs to be a concerted effort for groups to either have an exit strategy or a plan on how project will be sustained and delivered for the benefit of the NRA residents.

Another priority is also to ensure that the Partnership remains a strong group in the vacuum of knowing whether or not the powers will ever transfer from Central Government to Councils.  Whilst this does not hamper the role of the Partnership there is still some ambiguity as to when or if powers will transfer, which is somewhat unsettling for many partners engaged in the process.  MUDC are continuing to prepare the ground to enable any possible transfer to be seamless in that the local community are least affected by any potential changes in the delivery of a poverty/deprivation programme. Community Planning remains the priority focus for delivery over the next year and ahead along with the People and Place Neighbourhood Renewal Strategy Review involving co-design of new policy and partnership structures.

Attendance at sub group and partnership meetings has seen a decline in 2022/2023, particularly at community level. It has been challenging trying to encourage members to attend sub group and Partnership meetings with letters being issued to all members to ascertain whether they wish to remain on the partnership and sub groups.  DFC will work with the NR Coordinator to reengage with communities at local level and hopefully this will promote some reinvigorated efforts to engage as it is hoped that the structures in place will not fall in the possible last few years of the Programme.

Success of the NR Partnership in the 2022/2023 year was largely a result of the diligent work and commitment of those engaged in the NR process from both statutory and community and voluntary organisations with input from Councillors and external stakeholders.  In the years ahead it is hoped that we can continue to build connections through the NR Partnership and stand out as a good example of collaborative working.

Following the Covid 19 Pandemic and now dealing with the Cost of Living Crisis, it has been a major challenge for all of the partners involved in the NR Programme which the impact on the community resulting in looking at new way of programme and service delivery. This by far represents the greatest single issue in terms of impact on people’s lives for now and the immediate future, aside from the health consequences but also the resulting economic shock and its impact in terms of rising unemployment, increases in poverty and the recognised greater all round negative outcomes for areas of high deprivation.

Appendix 1

Appendix 2

Presentations at NR  Meetings April 2022- March 2023

PARTNERSHIP

- Levelling Up Funding bid for Gortgonis Community Health & Wellbeing Hug by Tony Morrison of Otium 26/05/22

- Levelling Up Funding bid for Dungannon Feeney Lane & Hill of The O’Neill by Alan McKeown of Food For Thought 26/05/22

- Verve Model Proposal by Sinead Taylor of SHSCT 29/09/22

- Coalisland Canal Update by Johnny McNeill of MUDC 24/11/22

- Make The Call Wraparound Service by Michael Gribben of DfC 24/11/22

HEALTH

1 	The Verve Health Living Network by Sinead Taylor SHSCT 28/09/22